## Sheet2
|  | 2016 | [11 empty] | 2017 | [11 empty] | 2018
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Seg 1-2 | orig | 2016 Feb: bid
| update | 2016 May: bid
Seg 3-4-5 | orig | 2016 Jan: 30%; 2018 Jan: construction (3-4 months? Clay conv. W Meg 4/16)
update

## schedule
Northern Walnut Creek |  |  | abbreviations: |  |  |  | MNA - Milwood Neighborhood Association, WXNA-Walnut Crossing Neighborhood Association, ARR-Austin Ridge Riders
Greenbelt Trail Project | [6 empty] | PM-Project Manager (City of Austin), WW-wastewater (sewer), WPRI-Waters Park Relief Interceptor
| 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Original Scope Balcones Park to Walnut Creek Park
original contract | 2010 May: construction schedule
Ph1 Mopac to Walnut Creek Park
original | 2011 Jun: design (redesign); 2011 Nov: bid; 2012 Mar: construction
actual | 2011 Jun: design (redesign); 2013 Feb: bid; 2013 Aug: construction; 2014 Sep: Phasing Change
Ph1A-segments 1-2 (combined with WPRI sewer project)
original | 2014 Sep: design; 2016 Jan: bid; 2016 Jun: construction ( 1 year for trail completion); 2017 Jul: + 6 mos sewer work
actual | 2016 Apr: bid; 2017 Dec: Dec 17 ? trail work complete
Ph1A-segments 3-5
original | 2017 Feb: construction (per 2/2/16 update)
actual | 2018 Apr: construction; 2018 Nov: time beyond initial schedule
[100 empty] | NTP |  |  | 2018-04-09
[100 empty] | 144 |  |  | 2018-08-31
[100 empty] | 180 |  |  | 2018-10-06
[92 empty] | estimated rain days | [7 empty] | 10 |  |  | 2018-10-16
Note on S8: contractor terminated
Note on AB11: per email R.Duane 6/13/11
Note on A12: project revised to delete Mopac to Balcones Park portion in Sept 2014. This portion is now called Ph 1A (segments 1-5)
Note on AM12: 2/14/13 award
Note on AO12: 4/22/13 Notice to Proceed
Note on AS12: Aug'13 Construction starts - completion expected summer 2014
Note on BF12: Sept 2014 - portion west of mopac removed from project - due to WW project and Salamander ESA issues. PM later states project will use up the entire budget - even with ~20% of the project deleted
Note on BZ12: grand opening set for 5/21 with only part of the original project complete
Note on A15: Mopac to Balcones Park Ballfield
Note on BN16: MNA, WXNA, ARR speak at COA Env.& Sustainability Comm. Mtg. request project to be expedited. PM discloses that project is "at budget" without completion Mopac to Balcones portion - meaning that Mopac to Walnut Creek has used all of the project funding.
Note on BW16: City agrees to include low flow conveyance at creek crossing.
Note on BY17: bid advertisement delayed for unknown reasons
Note on A19: Balcones Park Ball Field to Amherst
Note on BR20: City agrees to use neighborhood supported (and designed) switchback route in Balcones Park

## bid 1A
WPRI as on 5/17/16
Basic Information
Type: | Invitation For Bids (IFB)
Status: | Open
Due date extended from prior to 05/12/2016 09:30 AM, to prior to 05/26/2016 09:30 AM.
Open date extended from 05/12/2016 01:30 PM, to 05/26/2016 01:30 PM.
Solicitation Number: | IFB 6100 CLMC577
Description: | Waters Prk Relief Main/Southern Portion- Northern WC Tr Ph1A
Summary: | Construction of approximately 3,357 Linear feet of 36-inch and 34 linear feet of 42 inch waste water relief main with approximately 564 linear feet of trench less installation, and 17 polymer concrete manholes. Other work includes 12,095 sy of HMAC mill and overlay, 18,725 sf of concrete bike trail, bypass pumping, abandoning existing wastewater lines, storm water pipe relocation, erosion and sedimentation control, tree protection, traffic control, re-vegetation, sidewalk, curb & gutter, driveway repairs, and miscellaneous work.
Estimated Amount for Solicitation: | 6723350